## Sprint-1
SPRINT -1 : FEB 24TH - FEB 28TH
Task | Task Owner | Start Hour | Story Points-Day 1 | Story Points-Day 2 | Story Points-Day 3 | Story Points-Day 4 | Story Points-Day 5 | Total Hours
Task1: Review Requirements | MP/PH/AJ/RT | 3 | 1 | 1 | 1 | 0 | 0 | 3
Task2:Decide on Technology stack | MP/PH/AJ/RT | 1 | 0 | 0 | 1 | 0 | 0 | 1
Task3: Data modelling | MP/PH/AJ/RT | 3 | 0 | 0 | 0 | 2 | 1 | 3
Task3:Wireframes | MP/PH/AJ/RT | 3 | 0 | 0 | 0 | 2 | 1 | 3
Actual Remaining Hours |  | 10 | 9 | 8 | 6 | 2 | 0
Estimated RemainingHours |  | 10 | 8 | 6 | 4 | 2 | 0
|  |  |  | Team Member Name | Prarthana | Manasi | Rimzim | Akanksha
|  |  |  | What did I do since the last SCRUM meeting? | - | - | - | -
|  |  |  | What I plan to do this week? | Req Analysis,Wireframes, Database Creation | Req Analysis,Wireframes | Req Analysis,Wireframes | Req Analysis,Wireframes
|  |  |  | What Blockers do I have? | - | - | - | -
XP Core Values | Team
Communication | The team communicated via zoom meeting to discuss the requirements and the UI Wire frames.

## Sprint-2
SPRINT -2 : MARCH 2ND - 6TH
Task | Task Owner | Start Hour | Story Points-Day 1 | Story Points-Day 2 | Story Points-Day 3 | Story Points-Day 4 | Story Points-Day 5 | Total Hours
Task1: Home Screen and Admin Login | PH | 3 | 1 | 1 | 1 | 0 | 0 | 3
Task2:Reservation screen - update to wireframe and table modification. | MP | 3 | 1 | 1 | 1 | 0 | 0 | 3
Task3: Customer Sign up functionality- UI | PH | 3 | 0 | 0 | 1 | 1 | 1 | 3
Task4:Design the screen to view the vehicles | RT | 3 | 0 | 1 | 1 | 0 | 0 | 3
Task5:Work on location and vehicle tables | AJ | 3 | 0 | 1 | 0 | 1 | 1 | 3
Actual Remaining Hours |  | 15 | 12 | 8 | 4 | 2 | 0
Estimated RemainingHours |  | 15 | 12 | 9 | 6 | 3 | 0
|  |  |  | Team Member Name | Prarthana | Manasi | Rimzim | Akanksha
|  |  |  | What did I do since the last SCRUM meeting? | Created Database structure, Worked on Wireframes | Created wireframes for user module and Requirement analysis of reservation section of user module | Design wireframes and databases as a part of project setup | Created wireframes for vehicle and location related screens.
|  |  |  | What I plan to do for rest of sprint? | Design Home and Login Screens. Build UI for Customer Signup functionality | Updated the reservation wireframes and database tables for user module according to requirement. | Design view available vehicles screen | Define the tables and columns for vehicles and locations
|  |  |  | What Blockers do I have? | - | Pick up time and drop time requirement clarification | Design of table to store and retrieve the bookings. | -
XP Core Values | Team
Communication | The team communicated via zoom meeting to discuss the database table structures and the wireframes created by each team member.

## Sprint-3
SPRINT 3: MARCH 9TH - 13TH
Task | Task Owner | Start Hour | Story Points-Day 1 | Story Points-Day 2 | Story Points-Day 3 | Story Points-Day 4 | Story Points-Day 5 | Total Hours
Task1: Admin Dashboard Design | PH | 3 | 1 | 1 | 1 | 0 | 0 | 3
Task2:Admin Sign up | PH | 1 | 0 | 0 | 0 | 0 | 1 | 1
Task3:Rent Location Add/Delete/Update fuctionality | AJ | 3 | 1 | 1 | 1 |  |  | 3
Task4:Create query to fetch vehicle records for the filters | RT | 5 | 0 | 0 | 2 | 1 | 2 | 5
Task 5: Create reservation screen UI and update related tables. | MP | 3 | 0 | 1 | 1 | 1 | 0 | 3
Actual Remaining Hours |  | 15 | 13 | 10 | 5 | 3 | 0
Estimated RemainingHours |  | 15 | 12 | 9 | 6 | 3 | 0
|  |  |  | Team Member Name | Prarthana | Manasi | Rimzim | Akanksha
|  |  |  | What did I do since the last SCRUM meeting? | Worked on signing up new customer and Login for the Admin | modified the reservation table according to requirements. Updated the reservation wireframes to include certain requirements that were missed out previously. | Design the screen to view the vehicles | Updated location and vehicle tables. Worked on rental location jsp pages.
|  |  |  | What I plan to do for rest of sprint? | Admin sign up and design admin dashboard | create reservation UI screen and update related tables. | Design view available vehicles screen, create query to fetch the vehicle records | Build location functionality to add/delete/update rental locations.
XP Core Values | Team |  |  | What Blockers do I have? | - | - | - | -
Communication | The team members set up meetings via zoom whenever they had to communicate with another team member fo clarification.

## Sprint-4
SPRINT 4: MARCH 16TH - 20TH
Task | Task Owner | Start Hour | Story Points-Day 1 | Story Points-Day 2 | Story Points-Day 3 | Story Points-Day 4 | Story Points-Day 5 | Total Hours
Task-1 : Customer Login Screen | PH | 2 | 2 | 0 | 0 | 0 | 0 | 2
Task-2 : Vehicle classes based on factory pattern | AJ | 2 | 1 | 0 | 0 | 0 | 1 | 2
Task 3:Business Logic for reserve screen | MP | 3 | 1 | 1 | 1 | 0 | 0 | 3
Task4:create reservation Details UI screen | MP | 3 | 0 | 0 | 0 | 1 | 2 | 3
Task 5: Code changes to pass parameters to reservation screen | RT | 5 | 3 | 0 | 0 | 1 | 1 | 5
Task 5: Create query to fetch vehicle records for any location | RT | 3 | 0 | 0 | 0 | 1 | 2 | 3
Task 6: Database Changes to Vehicle Type Object. Design UI to display available Vehicle Types | PH | 2 | 0 | 0 | 0 | 0 | 2 | 2
Actual Remaining Hours |  | 20 | 13 | 12 | 11 | 8 | 0
Estimated RemainingHours |  | 20 | 16 | 12 | 8 | 4 | 0
|  |  |  | Team Member Name | Prarthana | Manasi | Rimzim | Akanksha
|  |  |  | What did I do since the last SCRUM meeting? | Worked on signing up the admin and designed the admin dashboard | created reserve UI screen and update related tables for changes as asked by RT | Design view available vehicles screen, create query to fetch the vehicle records | Worked on add, update, delete and read the rental locations.
|  |  |  | What I plan to do for rest of sprint? | Build screen for customer login. | create reservation Details UI screen and business logic for reserve screen. | create query to fetch the vehicle records at any location and code changes to pass parameters to reservation screen. | Work on vehicles classes and try to apply factory pattern
|  |  |  | What Blockers do I have? | - | - | - | -
XP Core Values | Team
Communication | The team set up meetings via zoom to communicate the changes made in table structures.

## Sprint-5
SPRINT 5: MARCH 23RD - 27TH
Task | Task Owner | Start Hour | Story Points-Day 1 | Story Points-Day 2 | Story Points-Day 3 | Story Points-Day 4 | Story Points-Day 5 | Total Hours
Task-1 : Add/Edit/Remove Vehicle Types | PH | 3 | 1 | 0 | 0 | 1 | 1 | 3
Task-2 : Get details and populate the reserve screen | MP | 3 | 2 | 0 | 0 | 0 | 1 | 3
Task 3: Find date time picker compatible for all browsers. | RT | 3 | 1 | 0 | 0 | 2 | 0 | 3
Task4:Work on add and update for vehicles, and fine tune. | AJ | 3 | 1 | 2 | 0 | 0 | 0 | 3
Task5:Update Customer Login servlet to pass username to Customer Landing Page. | PH | 1 | 1 | 0 | 0 | 0 | 0 | 1
Actual Remaining Hours |  | 13 | 7 | 5 | 5 | 2 | 0
Estimated RemainingHours |  | 13 | 10.4 | 7.8 | 5.2 | 2.6 | 0
|  |  |  | Team Member Name | Prarthana | Manasi | Rimzim | Akanksha
|  |  |  | What did I do since the last SCRUM meeting? | Worked on Customer Login and made changes to Vehicle Types table structure. | created reservation Details UI screen and updated reservation table | create query to fetch the vehicle records at any location. code changes to pass parameters to reservation screen | Worked on Vehicle List/delete functionality
|  |  |  | What I plan to do for rest of sprint? | Build logic for adding/editing and viewing vehicle Types | Get details and populate the reserve screen | Find date time picker compatible for all browsers. | Work on add and update for vehicles, and fine tune.
|  |  |  | What Blockers do I have? | - | - | - | -
XP Core Values | Team
Communication | The team members set up meetings with other team members whenever there were any blockers.

## Sprint-6
SPRINT 6: MARCH 30th - APRIL 3rd
Task | Task Owner | Start Hour | Story Points-Day 1 | Story Points-Day 2 | Story Points-Day 3 | Story Points-Day 4 | Story Points-Day 5 | Total Hours
Task-1 : Fine tune the vehicle type add/update/deletion | PH | 2 | 2 | 0 | 0 | 0 | 0 | 2
Task-2 : Perform Data validations and fine tune vehicle and location functionality | AJ | 3 | 1 | 1 | 0 | 1 | 0 | 3
Task-3:Testing for all the scenarios. | RT | 5 | 2 | 0 | 1 |  | 2 | 5
Task-4:Get details and populate the resesrvationdetails screen | MP | 5 | 0 | 3 | 1 | 1 | 0 | 5
Actual Remaining Hours |  | 15 | 10 | 6 | 4 | 2 | 0
Estimated RemainingHours |  | 15 | 12 | 9 | 6 | 3 | 0
|  |  |  | Team Member Name | Prarthana | Manasi | Rimzim | Akanksha
|  |  |  | What did I do since the last SCRUM meeting? | Worked on updating Customer Login to pass Customer Username and worked on building Vehicle Type Functionality | Get details and populate the reserve screen | Worked on Finding date time picker compatible for all browsers. | Add/update vehicle functionality for admin
|  |  |  | What I plan to do for rest of sprint? | Continue finetuning the Vehicle Type Functionality | Get details and populate the resesrvationdetails screen | Testing for all the scenarios.And finetuning date time picker. | Perform data validations and fine tune.
XP Core Values | Team |  |  | What Blockers do I have? | - | - | - | -
Communication | The team communicated regarding any issues that they were facing to get suggestions from other team members.

## Sprint-7
SPRINT 7: APRIL 6TH - 10TH
Task | Task Owner | Start Hour | Story Points-Day 1 | Story Points-Day 2 | Story Points-Day 3 | Story Points-Day 4 | Story Points-Day 5 | Total Hours
Task-1 : Build the screen to display list of customers that admin can activate/terminate | PH | 3 | 0 | 0 | 0 | 0 | 3 | 3
Task 2: Fine-tuning both reserve and reservationDetials screens | MP | 3 | 0 | 2 | 0 | 1 |  | 3
Task 3: Testing both reserve and reservationDetials screens | MP | 3 | 0 | 0 | 0 | 0 | 3 | 3
Task 4: Admin screen for updating fees and late charges | PH | 3 | 0 | 0 | 0 | 2 | 1 | 3
Task 5: Finish integration and test with other admin functionality end to end | AJ | 3 | 0 | 0 | 0 | 2 | 1 | 3
Task 6:Build a navigation page for managing booking and make a new reservation. | RT | 5 | 1 | 2 | 0 | 1 | 1 | 5
Actual Remaining Hours |  | 20 | 19 | 15 | 15 | 9 | 0
Estimated RemainingHours |  | 20 | 16 | 12 | 8 | 4 | 0
|  |  |  | Team Member Name | Prarthana | Manasi | Rimzim | Akanksha
|  |  |  | What did I do since the last SCRUM meeting? | Worked on fine tuning the add/edit/delete vehicle types functionality | Get details and populate the resesrvationdetails screen | Testing for all the scenarios and Finding date time picker compatible for all browsers. | Perform data validation and test Vehicle capacity check is added.
|  |  |  | What I plan to do for rest of sprint? | Will work on building admin functionality to activate and terminate customers | Fine-tuning and testing both screens. | Build a navigation page for managing booking and make a new reservation. | Fine tune, finish integration and test end to end.
|  |  |  | What Blockers do I have? | - | - | - | -
XP Core Values | Team
Communication | The team communicated regarding any functinality changes that would be affect other modules.

## Sprint-8
SPRINT 8: APRIL 13TH - 17TH
Task | Task Owner | Start Hour | Story Points-Day 1 | Story Points-Day 2 | Story Points-Day 3 | Story Points-Day 4 | Story Points-Day 5 | Total Hours
Task-1 : Autopopulate Vehicle Type in Vehicle Edit Screen and Unit Testing | PH | 2 | 2 | 0 | 0 | 0 | 0 | 2
Task 2: Integration of Search Vehicles and Reservation functionality. | RT | 3 | 0 | 0 | 0 | 1 | 2 | 3
Task 3: Integration with other modules and test end to end | AJ | 3 | 0 | 1 | 0 | 0 | 2 | 3
Task 4: Integration with Search functionality of RT and testing booking functionality | MP | 5 | 0 | 0 | 0 | 2 | 3 | 5
Actual Remaining Hours |  | 13 | 11 | 10 | 10 | 7 | 0
Estimated RemainingHours |  | 13 | 10.4 | 7.8 | 5.2 | 2.6 | 0
|  |  |  | Team Member Name | Prarthana | Manasi | Rimzim | Akanksha
|  |  |  | What did I do since the last SCRUM meeting? | Worked on customer display screen and updating late fees and registration amount. | Fine-tuning and testing both screens. | Build a navigation page for managing booking and make a new reservation. | Finish integration and test with other admin functionality. Added auto populate for edit vehicles on location. Finished edit vehicle module issues.
|  |  |  | What I plan to do for rest of sprint? | Auto population of Vehicle Type in Vehicle Edit Screen and Unit Testing. | Integrating with Search functionality of RT and testing booking functionality. | Integration of Search Vehicles and Reservation functionality. | Integrate with other modules and test end to end.
XP Core Values | Team |  |  | What Blockers do I have? | - | - | - | -
Communication | The team members set up meetings via zoom to integrate functinality of common modules.

## Sprint-9
SPRINT 9: APRIL 20TH - 24TH
Task | Task Owner | Start Hour | Story Points-Day 1 | Story Points-Day 2 | Story Points-Day 3 | Story Points-Day 4 | Story Points-Day 5 | Total Hours
Task-1 : Integration and Unit Testing | PH | 2 | 1 | 1 | 0 | 0 | 0 | 2
Task 2: Finetuning Search Functionality and Unit Testing | RT | 2 | 0 | 0 | 2 | 0 | 0 | 2
Task 3: End to end testing | AJ | 2 | 0 | 1 | 0 | 0 | 1 | 2
Task 4: Fixing bugs and finetuning | MP | 2 | 0 | 0 | 0 | 2 | 0 | 2
Actual Remaining Hours |  | 8 | 7 | 5 | 3 | 1 | 0
Estimated RemainingHours |  | 8 | 6.4 | 4.8 | 3.2 | 1.6 | 0
|  |  |  | Team Member Name | Prarthana | Manasi | Rimzim | Akanksha
|  |  |  | What did I do since the last SCRUM meeting? | Integration of admin module and bug fixes | Integration of Customer functionality | Fixed bugs in search and reservation functionality | Integration of admin module and bug fixes
|  |  |  | What I plan to do for rest of sprint? | Complete Integration and end to end testing. | Fine tuning and bug fixes | End to end testing and bug fixes | End to end testing and bug fixes
|  |  |  | What Blockers do I have? | - | - | - | -
XP Core Values | Team
Communication | The team set up meetings via zoom to integrate all the modules of the project and conducted integration testing.

## Sprint-10
SPRINT 10: APRIL 27TH - MAY 1ST
Task | Task Owner | Start Hour | Story Points-Day 1 | Story Points-Day 2 | Story Points-Day 3 | Story Points-Day 4 | Story Points-Day 5 | Total Hours
Task-1 : Hosting the project on EC2 | PH | 5 | 1 | 1 | 0 | 3 | 0 | 5
Task 2: Fixing minor bugs and E2E testing | RT | 2 | 0 | 1 | 0 | 0 | 1 | 2
Task 3: End to end testing and minor bug fixes | MP | 2 | 0 | 1 |  | 0 | 1 | 2
Task 4: End to end testing | AJ | 2 | 0 | 0 | 0 | 0 | 2 | 2
Actual Remaining Hours |  | 11 | 10 | 7 | 7 | 4 | 0
Estimated RemainingHours |  | 11 | 8.8 | 6.6 | 4.4 | 2.2 | 0
|  |  |  | Team Member Name | Prarthana | Manasi | Rimzim | Akanksha
|  |  |  | What did I do since the last SCRUM meeting? | Integration and unit testing | Finetuning the reservation functionality | Finetuning search functionality | End to end testing
|  |  |  | What I plan to do for rest of sprint? | Hosting on EC2 | End to end testing and bug fixes | End to end testing and bug fixes | Complete testing after deployment.
|  |  |  | What Blockers do I have? | - | - | - | -
| XP Core Values | Team
| Communication | The team set up meetings via zoom for testing the project end to end after deploying the application to EC2 server.